## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
All tasks committed in Sprint 1 were discussed during planning. Team communication was clear and consistent throughout the sprint. | The Admin Page UI was not completed within the sprint timeline. | Break large user stories like Admin Page into smaller sub-tasks during planning. | Re-estimate Admin Page sub-tasks and add to Sprint 2 backlog with story points. | Example
Roles were clearly defined — PO, Scrum Master, and Developer had no overlap in responsibilities. | MySQL database schema was modified mid-sprint, requiring rework on backend API routes. | Finalize and freeze the database schema before sprint coding begins. | PO and Developer to sign off on DB schema before Sprint 2 Day 1.
React.js frontend for the Landing Page and Student Dashboard was completed successfully. | Unit tests were not written for any of the completed features during Sprint 1. | Adopt a test-as-you-code approach — write at least 2 test cases per feature during development. | Add 'Write Test Cases' as a mandatory sub-task for every user story from Sprint 2 onwards.
Git branching strategy (feature branches + pull requests) was followed — no merge conflicts. | MS Planner board was not updated in real time — some tasks remained in 'To Do' even after completion. | Assign Scrum Master to verify and update the board daily before the standup meeting. | Scrum Master to do a board review every evening and send a summary to the team.
Node.js + Express REST API for task listing endpoint was built and tested with Postman. | Two tasks were blocked for 2 days due to dependency on the Admin module not being ready. | Identify task dependencies during sprint planning and sequence work accordingly. | Add a dependency field to each MS Planner card during the sprint planning session.
PO communicated requirement clarifications within 24 hours whenever developers raised queries. | Acceptance criteria were communicated verbally — no written document was shared with the team. | PO to prepare a written acceptance criteria document for each user story before sprint starts. | Create an acceptance criteria template in Google Drive and fill it before Sprint 2 begins.
Daily standups were held consistently. All team members attended every session on time. | No mid-sprint retrospective was held — issues were identified only at the end of the sprint. | Schedule a brief mid-sprint check-in on Day 7 of every sprint to surface blockers early. | Add a mid-sprint sync event to MS Planner calendar for all future sprints.